## Sheet1
Sprint Schedule (Planning and Monitoring Report) CS 4310 Software Eng. I: Requirements Engineering Computer Science Department The University of Texas at El Paso
Team member name | Number | Initials | Role Name
Joel Martinez | 1 | JZ | Team Leader (TL) |  |  | Team Leader
Jorge Magaña | 2 | JA | Planning Manager (PM) |  |  | Planning Manager
Epifanio Sarinana | 3 | EA | Quality Manager (QM) |  |  | Quality Manager
Isaac Zarate | 4 | IE | Support Manager (SM) |  |  | Support Manager
Caitlin Gregory | 5 | CY | Customer Interface Manager (CIM) |  |  | Customer Interface M
Ugyen Dorji | 6 | UI | Behavior Manager (BM) |  |  | Behavior Manager
Damien Pimentel | 7 | DL | Data-Flow & Business Manager (DBM) |  |  | Data-Flow & Business
Dylan Andrade | 8 | DE | Analyst Manager (AM) |  |  | Manager
| 9 |  |  |  |  | Analyst Manager
Week ##
| Work Time (hours: mins) |  | Deadline (mm/dd/yyyy) |  |  | Intended member work time (hours: mins) | [8 empty] | Actual member work time (hours: mins)
| Plan | Actual | Plan | Actual | Schedule Slip | Member 1 Initials | Member 2 Initials | Member 3 Initials | Member 4 Initials | Member 5 Initials | Member 6 Initials | Member 7 Initials | Member 8 Initials | Member 9 Initials | Member 1 Initials | Member 2 Initials | Member 3 Initials | Member 4 Initials | Member 5 Initials | Member 6 Initials | Member 7 Initials | Member 8 Initials | Member 9 Initials
[6 empty] | JZ | JA | EA | IE | CY | UI | DL | DE |  | JZ | JA | EA | IE | CY | UI | DL | DE
TF-25 - Tracks process structure, manages sections and document logistics. | 16 | 1 | 2025-09-17 | 2025-09-15 | 0 | DE: 16:00 | [8 empty] | 1:00 |  | <--- | The values in this row are examples.
TF-24 - Focuses on aligning use cases with business logic and requirements. | 16 | 3 | 2025-09-17 | 2025-09-15 | 0 | DL: 16:00 | [7 empty] | 3:00
TF-23 - Focuses on behavior and functional interactions within scenarios. | 16 | 3.5 | 2025-09-17 | 2025-09-15 | 0 | UI: 16:00 | [6 empty] | 3:30
TF-22 - Responsible for customer roles, actor identification, and clarity. | 16 |  | 2025-09-17 | 2025-09-15 | 0 | CY: 16:00
TF-21 - Supports with diagram tools, formatting, and file structure. | 16 | 3 | 2025-09-17 | 2025-09-15 | 0 | IE: 16:00 |  |  |  |  | 3:00
TF-20 - Reviews and verifies all content for completeness and formatting. | 16 | 4 | 2025-09-17 | 2025-09-15 | 0 | EA: 16:00 |  |  |  | 4:00
TF-19 - Owns planning/logistics, supports use case structure. | 16 | 8 | 2025-09-17 | 2025-09-15 | 0 | JA: 16:00 |  |  | 8:00
TF-18 - Work Item - Coordinates collaboration, ensures the entire document is completed and submitted on time. | 16 | 8 | 2025-09-17 | 2025-09-15 | 0 | JZ: 16:00 |  | 8:00
Total Time: | 0.25 | 0.25347 |  |  | 0 | 0:40 | 0:40 | 0:40 | 0:40 | 0:40 | 0:40 | 0:40 | 0:40 | 0:40 | 0:55 | 0:55 | 0:45 | 0:55 | 0:20 | 0:55 | 0:55 | 0:00 | 0:25
Team performance Analysis
Balanced work effort distribution | The initial plan allocated 16 hours per team member to ensure an even distribution of responsibilities across all critical tasks. However, actual effort varied significantly, with Dylan Andrade completing his task in just 1 hour and others like Jorge Magana and Joel Martinez dedicating 8 hours each, reflecting a pragmatic adjustment based on task complexity and emerging needs. This flexible approach allowed for efficient resource utilization while maintaining coverage of all key areas. 2)
Meeting internal and hard due dates | We implemented staggered deadlines to manage workload and enable iterative reviews, allowing early completion of foundational sections to inform subsequent tasks. This cadence facilitated continuous feedback loops and timely adjustments, ensuring alignment with overall project goals without overwhelming the team at any single point. The strategy balanced progress visibility with manageable checkpoints. 3)
High quality of work submitted | Rework was minimal but noted in TF-25, where Dylan Andrade reported limited activity, suggesting potential underutilization or task scope misalignment. This affected process structure and document logistics sections, prompting a review to better define responsibilities and ensure comprehensive coverage in future cycles. Overall, rework did not significantly impact project timelines or quality.
List of problems (unbalanced effort, poor estimation, missing due dates, poor work quality, others) | <Problem 1 name>; <problems description> <corrective action, if any>
[TF-25] Test Comment for issue logging: felt like I didnt do much for Joel
Member performnace for this assignment |  | Waiver |  | The % for each member's participation is earned each week and starts at 0%. Each member is expected to attend and actively participate in all meetings, do all assigned tasks with high quality, do your role responsibilities, and support the team to earn 100%. The team may give a waiver to a member when he/she negotiates less effort this week before any internal due date has passed. Member is expected to retribute effort in following weeks. | bar: JZ to IE
oscar | Joel Martinez: 92/100 - GPT disabled; score set manually. | N | bar: JZ to IE
adrian | Jorge Magaña: 92/100 - GPT disabled; score set manually. | Y | bar: JZ to IE
0 | Epifanio Sarinana: 92/100 - GPT disabled; score set manually. | N | bar: JZ to IE
0 | Isaac Zarate: 92/100 - GPT disabled; score set manually. | N | bar: JZ to IE
0 | Caitlin Gregory: 92/100 - GPT disabled; score set manually. | N | bar: JZ to IE
0 | Ugyen Dorji: 92/100 - GPT disabled; score set manually. | N
0 | Damien Pimentel: 92/100 - GPT disabled; score set manually. | N
0 | Dylan Andrade: 92/100 - GPT disabled; score set manually. | N
0 |  | N